## Planner
Technician Name | Competency | Start Date | Duration (days) | End Date | Installation | Client | Status | Work Order | Support Classification | Scope
Ivan Heredia | Project Engineer | 2025-11-04 |  | 2025-11-06 | Veshi yard | SAIPEM | Onshore | 281008-01 | Expat | 100T Mobile crane certification
Ivan Heredia | Project Engineer | 2025-11-10 |  | 2025-11-14 | Veshi yard | SAIPEM | Onshore | 281008-04 | Expat | 300T Mobile crane certification
Ivan Heredia | Project Engineer | 2025-11-07 |  | 2025-11-09 | Veshi yard | SAIPEM | Onshore | 281008-02 | Expat | 60T Mobile crane certification
Ivan Heredia | Project Engineer | 2025-11-09 |  | 2025-11-09 | Veshi yard | SAIPEM | Onshore | 281008-02 | Expat | 60T Mobile crane certification
Erick Pena | Workleader | 2025-12-08 |  | 2025-12-10 | Normand Samson | Solstad | Offshore | 282001-04 | Expat | 6M Crane certification
Royhaizat Musa | API Crane Inspetor/Safety leader/Opito Rigger | 2025-12-08 |  | 2025-12-10 | Normand Samson | Solstad | Offshore | 282001-04 | Expat | 6M Crane certification
Alex Ali | Workleader | 2025-12-06 |  | 2026-01-03 | One Guyana | SBM Offshore | Offshore | 282000-42 | Regional | 6M LGI
Alex Ali | Workleader | 2026-01-03 |  | 2026-01-03 | Onshore | SBM Offshore | Travel | 282000-42 | Regional | 6M LGI
Alex Ali | Workleader | 2026-01-04 |  | 2026-01-04 | Onshore | SBM Offshore | Standby | 282000-42 | Regional | 6M LGI
Arul Franklin | EX engineer | 2026-01-15 |  | 2026-01-22 | Unity | SBM offshore | Offshore | 282000-75 | Expat | 6M LGI
Arul Franklin | EX engineer | 2026-01-24 |  | 2026-01-25 | Unity | SBM offshore | Travel | 282000-75 | Expat | 6M LGI
Britney Benjamin | Multiskilled rope access technician | 2025-12-08 |  | 2025-12-21 | Prosperity | SBM Offshore | Offshore | 282000-26 | Local | 6M LGI
Britney Benjamin | Multiskilled rope access technician | 2025-12-10 |  | 2025-12-20 | One Guyana | SBM Offshore | Offshore | 282000-42 | Local | 6M LGI
Darrel Cato | Multiskilled rope access technician | 2025-12-08 |  | 2025-12-22 | Prosperity | SBM Offshore | Offshore | 282000-26 | Local | 6M LGI
Darrel Cato | Multiskilled rope access technician | 2025-12-26 |  | 2026-01-12 | Destiny | SBM Offshore | Offshore | 282000-17 | Local | 6M LGI
Heriandy Rahim | Workleader | 2025-12-26 |  | 2026-01-12 | Destiny | SBM Offshore | Offshore | 282000-17 | Expat | 6M LGI
Jesus Estrada | Workleader | 2025-12-08 |  | 2025-12-22 | Prosperity | SBM Offshore | Offshore | 282000-26 | Expat | 6M LGI
Jesus Estrada | Workleader | 2026-01-05 |  | 2026-01-22 | Unity | SBM Offshore | Offshore | 282000-75 | Expat | 6M LGI
Lee Poh Chew | Safety Leader | 2025-12-08 |  | 2025-12-22 | Prosperity | SBM Offshore | Offshore | 282000-26 | Expat | 6M LGI
Lee Poh Seng | Safety Leader | 2025-12-06 |  | 2025-12-27 | One Guyana | SBM Offshore | Offshore | 282000-42 | Expat | 6M LGI
Leonardo Gonzaga | Multiskilled rope access technician | 2025-12-06 |  | 2025-12-27 | One Guyana | SBM Offshore | Offshore | 282000-42 | Expat | 6M LGI
Nicholas Ramlogan | Multiskilled rope access technician | 2026-01-05 |  | 2026-01-22 | Unity | SBM Offshore | Offshore | 282000-75 | Local | 6M LGI
Nio Ann Aik | Safety Leader | 2025-12-26 |  | 2026-01-12 | Destiny | SBM Offshore | Offshore | 282000-17 | Expat | 6M LGI
Alistair Narain | Field Engineer | 2025-12-03 |  | 2025-12-10 | One Guyana | SBM Offshore | Offshore | 282000-58 | Local | Annual elevator inspection
Alistair Narain | Field Engineer | 2025-12-28 |  | 2026-01-01 | Unity | SBM Offshore | Offshore | 281010-07 | Local | Annual elevator inspection
Alistair Narain | Field Engineer | 2025-11-17 |  | 2025-11-27 | Unity | SBM Offshore | Offshore | 281010-04 | Local | Annual crane inspection
Royhaizat Musa | API Crane Inspetor/Safety leader/Opito Rigger | 2025-11-17 |  | 2025-11-27 | Unity | SBM Offshore | Offshore | 281010-04 | Expat | Annual crane inspection
Alistair Narain | Field Engineer | 2025-12-06 |  | 2025-12-13 | One Guyana | SBM Offshore | Offshore | 282000-58 | Local | Annual elevator inspection
Alistair Narain | Field Engineer | 2025-12-29 |  | 2026-01-01 | Unity | SBM Offshore | Offshore | 282000-76 | Local | Annual elevator inspection
Alistair Narain | Field Engineer | 2026-01-03 |  | 2026-01-07 | One Guyana | SBM Offshore | Offshore | 282000-58 | Local | Annual elevator inspection
Houssam Zamman | Elevator Engineer | 2025-12-04 |  | 2025-12-05 | One Guyana | SBM Offshore | Travel | 282000-58 | Expat | Annual elevator inspection
Houssam Zamman | Elevator Engineer | 2025-12-06 |  | 2025-12-13 | One Guyana | SBM Offshore | Offshore | 282000-58 | Expat | Annual elevator inspection
Houssam Zamman | Elevator Engineer | 2025-12-14 |  | 2025-12-14 | One Guyana | SBM Offshore | Travel | 282000-58 | Expat | Annual elevator inspection
Yousef Alqhaiwi | Elevator Engineer | 2025-12-27 |  | 2025-12-28 | Unity | SBM Offshore | Travel | 282000-76 | Expat | Annual elevator inspection
Yousef Alqhaiwi | Elevator Engineer | 2025-12-29 |  | 2026-01-01 | Unity | SBM Offshore | Offshore | 282000-76 | Expat | Annual elevator inspection
Yousef Alqhaiwi | Elevator Engineer | 2026-01-02 |  | 2026-01-02 | Unity | SBM Offshore | Onshore | 282000-76 | Expat | Annual elevator inspection
Yousef Alqhaiwi | Elevator Engineer | 2026-01-03 |  | 2026-01-07 | One Guyana | SBM Offshore | Offshore | 282000-58 | Expat | Annual elevator inspection
Yousef Alqhaiwi | Elevator Engineer | 2026-01-03 |  | 2026-01-10 | One Guyana | SBM Offshore | Offshore | 282000-58 | Expat | Annual elevator inspection
Britney Benjamin | Cclaw technician | 2026-01-15 |  | 2026-01-19 | Unity | SBM Offshore | Offshore |  | Local | Cclaws
Britney Benjamin | Cclaw technician | 2026-02-12 |  | 2026-02-16 | Prosperity | SBM Offshore | Offshore |  | Local | Cclaws
Ivan Heredia | Project Engineer | 2026-01-15 |  | 2026-01-19 | Unity | SBM Offshore | Offshore |  | Expat | Cclaws
Ivan Heredia | Project Engineer | 2026-02-12 |  | 2026-02-16 | Prosperity | SBM Offshore | Offshore |  | Expat | Cclaws
Cahill Tanner | Workleader | 2026-03-14 |  | 2026-03-18 | One Guyana | SBM offshore | Offshore | 281013-02 | Expat | Container transfer
Dane Matthysen | Rigger | 2026-03-14 |  | 2026-03-18 | One Guyana | SBM offshore | Offshore | 281013-02 | Expat | Container transfer
Raúl Almeida | Multiskilled rope access technician | 2026-03-14 |  | 2026-03-18 | One Guyana | SBM offshore | Offshore | 281013-02 | Expat | Container transfer
Shameer Chester | Multiskilled rope access technician | 2026-03-14 |  | 2026-03-18 | One Guyana | SBM offshore | Offshore | 281013-02 | Local | Container transfer
Alex Ali | Workleader | 2025-11-04 |  | 2025-12-05 | Don Taylor | Noble | Offshore | 281001-09 | Regional | Contractual scopes
Alex Ali | Workleader | 2026-01-05 |  | 2026-01-05 | Onshore | Noble | Travel | 281001-09 | Regional | Contractual scopes
Alex Ali | Workleader | 2026-01-06 |  | 2026-02-03 | Don Taylor | Noble | Offshore | 281001-09 | Regional | Contractual scopes
Arul Franklin | EX engineer | 2025-12-16 |  | 2026-01-13 | Sam Croft | Noble | Offshore |  | Expat | Contractual scopes
Arul Franklin | EX engineer | 2026-02-10 |  | 2026-02-12 | Sam Croft | Noble | Travel |  | Expat | Contractual scopes
Arul Franklin | EX engineer | 2026-02-13 |  | 2026-03-13 | Sam Croft | Noble | Offshore |  | Expat | Contractual scopes
Heriandy Rahim | Workleader | 2025-11-21 |  | 2025-12-12 | Tom Madden | Noble | Offshore | 281002-09 | Expat | Contractual scopes
Cahill Tanner | Workleader | 2026-03-05 |  | 2026-03-12 | Unity | SBM offshore | Offshore | 282000-87 | Expat | Crane cylinder replacement
Dane Matthysen | Safety Leader | 2026-03-05 |  | 2026-03-12 | Unity | SBM offshore | Offshore | 282000-87 | Expat | Crane cylinder replacement
Raul Almeida | Multiskilled rope access technician | 2026-03-05 |  | 2026-03-12 | Unity | SBM offshore | Offshore | 282000-87 | Expat | Crane cylinder replacement
Shameer Chester | Multiskilled rope access technician | 2026-03-05 |  | 2026-03-12 | Unity | SBM offshore | Offshore | 282000-87 | Expat | Crane cylinder replacement
Hendrick Mallinson | Safety Leader/Opito rigger | 2026-02-12 |  | 2026-02-19 | Destiny | SBM offshore | Offshore | TBC | Expat | Crane Hose Replacement
Dillon Harry | PAUT | 2026-01-26 |  | 2026-01-29 | Prosperity | SBM Offshore | Offshore | 281010-15 | Local | Crane slew bolts tensioning
Kenneth Brandal | Crane Engineer | 2026-01-26 |  | 2026-01-29 | Prosperity | SBM Offshore | Offshore | 281010-15 | Expat | Crane slew bolts tensioning
Dillon Harry | PAUT | 2026-01-21 |  | 2026-01-24 | One Guyana | SBM Offshore | Offshore | 281010-16 | Expat | Crane slew bolts tensioning + PAUT
Kenneth Brandal | Crane Engineer | 2026-01-21 |  | 2026-01-24 | One Guyana | SBM Offshore | Offshore | 281010-16 | Expat | Crane slew bolts tensioning + PAUT
Akaysse de Silva | Multiskilled rope access technician | 2025-12-18 |  | 2026-01-08 | Unity | SBM Offshore | Offshore | 619078-91 | Local | DROPS
Huan Peng Whee | Safety Leader | 2025-12-18 |  | 2026-01-08 | Unity | SBM Offshore | Offshore | 619078-91 | Expat | DROPS
Syahrizan Khaidzir | Workleader | 2025-12-18 |  | 2026-01-08 | Unity | SBM Offshore | Offshore | 619078-91 | Expat | DROPS
Kenneth Brandal | Crane Engineer | 2026-02-20 |  | 2026-02-22 | Destiny | SBM offshore | Offshore | 282000-34 | Expat | Dumb waiter inspection
Ahmad Mazyadi | Workleader | 2025-11-16 |  | 2025-12-03 | Castorone | SAIPEM | Offshore | 257020-05 | Expat | eDROPS
Akaysse de Silva | Multiskilled rope access technician | 2025-11-16 |  | 2025-12-03 | Castorone | SAIPEM | Offshore | 257020-05 | Local | eDROPS
Jesus Estrada | Safety Leader | 2025-11-16 |  | 2025-12-03 | Castorone | SAIPEM | Offshore | 257020-05 | Expat | eDROPS
Ahmad Mazyadi | Workleader | 2026-03-05 | 16 | 2026-03-20 | FDS-2 | SAIPEM | Offshore | 257020-07 | Expat | eDROPS baseline
Akaysse de Silva | Multiskilled rope access technician | 2026-03-05 | 16 | 2026-03-20 | FDS-2 | SAIPEM | Offshore | 257020-07 | Local | eDROPS baseline
Raul Almeida | Rope acces safety leader | 2026-03-05 | 16 | 2026-03-20 | FDS-2 | SAIPEM | Offshore | 257020-07 | Expat | eDROPS baseline
Darrel Cato | Field Technician | 2026-02-23 |  | 2026-02-26 | Prosperity | SBM offshore | Offshore |  | Local | Elevator annual maintenance and inspection
Yousef Alqhaiwi | Elevator Engineer | 2026-02-23 |  | 2026-02-26 | Prosperity | SBM offshore | Offshore |  | Expat | Elevator annual maintenance and inspection
Darrel Cato | Field Technician | 2026-02-14 |  | 2026-02-16 | One Guyana | SBM offshore | Offshore | 281013-01 | Local | Elevator Repair
Yousef Alqhaiwi | Elevator Engineer | 2026-02-11 |  | 2026-02-12 | One Guyana | SBM offshore | Travel | 281013-01 | Expat | Elevator Repair
Yousef Alqhaiwi | Elevator Engineer | 2026-02-13 |  | 2026-02-13 | One Guyana | SBM offshore | Standby | 281013-01 | Expat | Elevator Repair
Yousef Alqhaiwi | Elevator Engineer | 2026-02-14 |  | 2026-02-21 | One Guyana | SBM offshore | Offshore | 281013-01 | Expat | Elevator Repair
Kenneth Brandal | Crane Engineer | 2026-02-17 |  | 2026-02-23 | Destiny | SBM offshore | Offshore | 281010-19 | Expat | Engine room crane survey
Lee Poh Chew | Safety Leader/Opito rigger | 2025-10-21 |  | 2025-11-28 | Don Taylor | Noble | Offshore | 281001-10 | Expat | Exhaust fans scope
Leonardo Gonzaga | Multiskilled rope access technician | 2025-11-21 |  | 2025-11-28 | Don Taylor | Noble | Offshore | 281001-10 | Expat | Exhaust fans scope
Nicholas Ramlogan | Multiskilled rope access technician | 2025-10-21 |  | 2025-11-28 | Don Taylor | Noble | Offshore | 281001-10 | Regional | Exhaust fans scope
Nio Ann Aik | Safety Leader/Opito rigger | 2025-10-21 |  | 2025-11-21 | Don Taylor | Noble | Offshore | 281001-10 | Expat | Exhaust fans scope
Akaysse de Silva | Multiskilled rope access technician | 2025-11-10 |  | 2025-11-13 | Prosperity | SBM Offshore | Offshore | 282000-35 | Local | Fall protection inspection
Paraisram Budhu | Multiskilled rope access technician | 2025-11-10 |  | 2025-11-13 | Prosperity | SBM Offshore | Offshore | 282000-35 | Local | Fall protection inspection
Britney Benjamin | Multiskilled rope access technician | 2025-11-22 |  | 2025-11-26 | Unity | SBM Offshore | Offshore | 282000-08 | Local | Flare boom survey
Britney Benjamin | Drone Pilot | 2026-02-02 |  | 2026-02-04 | One Guyana | SBM Offshore | Offshore |  | Local | Flare boom survey
Britney Benjamin | Drone Pilot | 2026-03-31 |  | 2026-04-02 | Destiny | SBM offshore | Offshore | 282000-81 | Local | Flare boom survey
Goran Bisko | 3D modeller | 2026-03-26 |  | 2026-04-02 | Destiny | SBM offshore | Offshore | 282000-81 | Expat | Flare boom survey
Oscar Fernandez | Drone Pilot | 2026-02-02 |  | 2026-02-04 | One Guyana | SBM Offshore | Offshore |  | Expat | Flare boom survey
Oscar Fernandez | Drone Pilot | 2026-02-08 |  | 2026-02-09 | One Guyana | SBM Offshore | Travel |  | Expat | Flare boom survey
Oscar Fernandez | Drone Pilot | 2026-03-31 |  | 2026-04-02 | Destiny | SBM offshore | Offshore | 282000-81 | Expat | Flare boom survey
Britney Benjamin | Multiskilled rope access technician | 2026-02-22 |  | 2026-03-09 | Destiny | SBM offshore | Offshore |  | Expat | GRE line repair
Ivan Heredia | Project Engineer | 2026-02-22 |  | 2026-03-09 | Destiny | SBM offshore | Offshore |  | Expat | GRE line repair
Darrel Cato | Multiskilled rope access technician | 2025-12-23 |  | 2025-12-25 | Destiny | SBM Offshore | Offshore | 282000-17 | Local | GTG100 Certification
Heriandy Rahim | Workleader | 2025-12-23 |  | 2025-12-25 | Destiny | SBM Offshore | Offshore | 282000-17 | Expat | GTG100 Certification
Nio Ann Aik | Safety Leader | 2025-12-23 |  | 2025-12-25 | Destiny | SBM Offshore | Offshore | 282000-17 | Expat | GTG100 Certification
Alistair Narain | Field Engineer | 2026-02-04 |  | 2026-02-04 | Onshore | SBM offshore | Onshore | TBC | Local | Hoist Inspection
Iván Heredia | Multiskilled rope access technician | 2026-02-04 |  | 2026-02-04 | Onshore | SBM offshore | Onshore | TBC | Expat | Hoist Inspection
Shameer Chester | Multiskilled rope access technician | 2026-02-04 |  | 2026-02-04 | Onshore | SBM offshore | Onshore | TBC | Local | Hoist Inspection
Lee Poh Chew | Multiskilled rope access technician | 2026-01-24 |  | 2026-01-31 | One Guyana | SBM offshore | Offshore |  | Local | Hoist removal/rope access
Lee Poh Seng | Safety Leader | 2026-01-24 |  | 2026-01-31 | One Guyana | SBM offshore | Offshore |  | Expat | Hoist removal/rope access
Syahrizan Khaidzir | Workleader | 2026-01-24 |  | 2026-01-31 | One Guyana | SBM offshore | Offshore |  | Expat | Hoist removal/rope access
Akaysse de Silva | Multiskilled rope access technician | 2026-02-05 |  | 2026-02-12 | Prosperity | SBM Offshore | Offshore | 282000-89 | Local | Hose reel pad eye certification
Ivan Heredia | Workleader | 2026-02-05 |  | 2026-02-12 | Prosperity | SBM Offshore | Offshore |  | Expat | Hose reel pad eye certification
Britney Benjamin | Multiskilled rope access technician | 2025-11-27 |  | 2025-12-01 | Unity | SBM Offshore | Offshore | 282000-57 | Local | Hull inspection survey
Britney Benjamin | Drone Pilot | 2026-01-28 |  | 2026-02-01 | One Guyana | SBM Offshore | Offshore | 282000-80 | Local | Hull inspection survey
Britney Benjamin | Drone Pilot | 2026-03-26 |  | 2026-03-30 | Destiny | SBM offshore | Offshore |  | Local | Hull inspection survey
Edwin Thomas | Frosio engineer | 2026-01-17 |  | 2026-01-19 | Onshore | SBM offshore | Travel | 282000-80 | Expat | Hull inspection survey
Edwin Thomas | Frosio engineer | 2026-01-20 |  | 2026-01-27 | Onshore | SBM offshore | Standby | 282000-80 | Expat | Hull inspection survey
Edwin Thomas | Frosio engineer | 2026-01-28 |  | 2026-01-31 | One Guyana | SBM Offshore | Offshore | 282000-80 | Expat | Hull inspection survey
Edwin Thomas | Frosio engineer | 2026-02-01 |  | 2026-02-02 | One Guyana | SBM Offshore | Travel | 282000-80 | Expat | Hull inspection survey
Edwin Thomas | Frosio engineer | 2026-03-26 |  | 2026-03-30 | Destiny | SBM offshore | Offshore |  | Expat | Hull inspection survey
Oscar Fernandez | Drone Pilot | 2026-01-26 |  | 2026-01-27 | Onshore | SBM offshore | Travel | 282000-80 | Expat | Hull inspection survey
Oscar Fernandez | Drone Pilot | 2026-01-28 |  | 2026-02-01 | One Guyana | SBM Offshore | Offshore | 282000-80 | Expat | Hull inspection survey
Oscar Fernandez | Drone Pilot | 2026-03-26 |  | 2026-03-30 | Destiny | SBM offshore | Offshore |  | Expat | Hull inspection survey
Daniel Henry | Multiskilled rope access technician | 2026-02-05 |  | 2026-02-06 | Onshore | Axess Glass Inc | Onshore | 28007-24 | Local | Inventory Control
Darrel Cato | Multiskilled rope access technician | 2026-02-05 |  | 2026-02-06 | Onshore | Axess Glass Inc | Onshore | 28007-24 | Local | Inventory Control
Jared Gonsalves | Multiskilled rope access technician | 2026-02-05 |  | 2026-02-06 | Onshore | Axess Glass Inc | Onshore | 28007-24 | Local | Inventory Control
Heriandy Rahim | Workleader | 2025-10-24 |  | 2025-11-15 | Tom Madden | Noble | Offshore | 281002-10 | Expat | Lifeboats inspection
Jaylano Toppin | Multiskilled rope access technician | 2025-11-22 |  | 2025-12-03 | One Guyana | SBM Offshore | Offshore | TBD | Regional | Maintenance scopes
Nio Ann Aik | Safety Leader/Opito rigger | 2025-11-22 |  | 2025-12-03 | One Guyana | SBM Offshore | Offshore | TBD | Expat | Maintenance scopes
Paraisram Budhu | Multiskilled rope access technician | 2025-11-22 |  | 2025-12-03 | One Guyana | SBM Offshore | Offshore | TBD | Local | Maintenance scopes
Akaysse de Silva | Multiskilled rope access technician | 2026-02-03 |  | 2026-02-03 | GYBSI | SBM offshore | Onshore | 282000-94 | Local | OGY PSV Container
Darrel Cato | Multiskilled rope access technician | 2025-10-22 |  | 2025-10-26 | Destiny | SBM Offshore | Offshore | 282000-64 | Local | Pad eyes certification
Alistair Narain | Field Engineer | 2026-02-03 |  | 2026-02-03 | Nexus | SBM offshore | Onshore | 281011-01 | Local | PTY - Rigging Loft
Daniel Henry | Multiskilled rope access technician | 2026-02-03 |  | 2026-02-03 | Nexus | SBM offshore | Onshore | 281011-01 | Local | PTY - Rigging Loft
Jared Gonsalves | Multiskilled rope access technician | 2026-02-03 |  | 2026-02-03 | Nexus | SBM offshore | Onshore | 281011-01 | Local | PTY - Rigging Loft
Akaysse de Silva | Multiskilled rope access technician | 2026-02-03 |  | 2026-02-03 | GYBSI | SBM offshore | Onshore | 282000-97 | Local | PTY Helifuel Inspection
Akaysse de Silva | Multiskilled rope access technician | 2026-02-04 |  | 2026-02-04 | GYBSI | SBM offshore | Onshore | 282000-98 | Local | PTY Racks Inspection
Darrel Cato | Multiskilled rope access technician | 2026-02-03 |  | 2026-02-04 | GYBSI | SBM offshore | Onshore | TBD | Local | Racks Inspection + Helifuel Tank + PSV Container
Leonardo Gonzaga | Multiskilled rope access technician | 2026-02-03 |  | 2026-02-04 | GYBSI | SBM offshore | Onshore | TBD | Expat | Racks Inspection + Helifuel Tank + PSV Container
Alex Ali | Workleader | 2026-02-04 |  | 2026-02-06 | Onshore | Axess Glass Inc | Onshore | 282007-24 | Regional | RAT Audit Preparation
Huan Peng Whee | Safety Leader |  |  |  | Prosperity | SBM offshore | Offshore |  | Expat | Remazel preservation
Ivan Heredia | Project Engineer |  |  |  | Prosperity | SBM Offshore | Offshore |  | Expat | Remazel preservation
Nicholas Ramlogan | Multiskilled rope access technician |  |  |  | Prosperity | SBM Offshore | Offshore |  | Regional | Remazel preservation
Ivan Heredia | Project Engineer | 2025-11-18 |  | 2026-01-13 | Onshore | Axess Glass Inc | Days Off | N/A | Expat | Rest period
Alistair Narain | Field Engineer | 2026-01-13 |  | 2026-01-14 | Unity | SBM offshore | Onshore | 282000-59 | Local | Rigging loft
Alistair Narain | Field Engineer | 2026-01-15 |  | 2026-01-16 | One Guyana | SBM offshore | Onshore | 282000-61 | Local | Rigging loft
Huan Peng Whee | Multiskilled rope access technician | 2026-01-13 |  | 2026-01-14 | Unity | SBM offshore | Onshore | 282000-59 | Expat | Rigging loft
Huan Peng Whee | Multiskilled rope access technician | 2026-01-15 |  | 2026-01-16 | One Guyana | SBM offshore | Onshore | 282000-61 | Expat | Rigging loft
Lee Poh Seng | Multiskilled rope access technician | 2026-01-13 |  | 2026-01-14 | Unity | SBM offshore | Onshore | 282000-59 | Expat | Rigging loft
Lee Poh Seng | Multiskilled rope access technician | 2026-01-15 |  | 2026-01-16 | One Guyana | SBM offshore | Onshore | 282000-61 | Expat | Rigging loft
Shameer Chester | Multiskilled rope access technician | 2026-01-13 |  | 2026-01-14 | Unity | SBM offshore | Onshore | 282000-59 | Local | Rigging loft
Shameer Chester | Multiskilled rope access technician | 2026-01-15 |  | 2026-01-16 | One Guyana | SBM offshore | Onshore | 282000-61 | Local | Rigging loft
Alex Ali | Workleader | 2026-02-07 |  | 2026-02-09 | One Guyana | Axess Glass Inc | Onshore | 282000-42 | Regional | Rigging loft Order and cleanliness
Alex Ali | Workleader | 2026-02-09 |  | 2026-02-09 | One Guyana | Axess Glass Inc | Travel | 282000-42 | Regional | Rigging loft Order and cleanliness
Alistair Narain | MRT technician | 2026-03-26 |  | 2026-04-06 | Destiny | SBM Offshore | Offshore | 281010-17 | Local | RPS crane maintenance
Raju Adhinarayanan | Multiskilled rope access technician with NDT | 2026-03-26 |  | 2026-04-06 | Destiny | SBM Offshore | Offshore | 281010-17 | Expat | RPS crane maintenance
Hendrick Mallinson | API Crane Inspetor/Safety leader/Opito Rigger | 2026-03-26 |  | 2026-04-06 | Destiny | SBM Offshore | Offshore | 281010-17 | Expat | RPS crane maintenance
Kenneth Brandal | Crane Engineer | 2026-03-26 |  | 2026-04-06 | Destiny | SBM Offshore | Offshore | 281010-17 | Expat | RPS crane maintenance
Kristoffer Thue | Crane Engineer | 2026-03-26 |  | 2026-04-06 | Destiny | SBM Offshore | Offshore | 281010-17 | Expat | RPS crane maintenance
Alistair Narain | Field Engineer | 2026-03-05 |  | 2026-03-25 | Destiny | SBM Offshore | Offshore | 281010-16 | Local | Topside davits maintenance
Raju Adhinarayanan | EX engineer | 2026-03-05 |  | 2026-03-25 | Destiny | SBM Offshore | Offshore | 281010-16 | Expat | Topside davits maintenance
Hendrick Mallinson | API Crane Inspetor/Safety leader/Opito Rigger | 2026-03-05 |  | 2026-03-25 | Destiny | SBM Offshore | Offshore | 281010-16 | Expat | Topside davits maintenance
Kenneth Brandal | Crane Engineer | 2026-03-05 |  | 2026-03-25 | Destiny | SBM Offshore | Offshore | 281010-16 | Expat | Topside davits maintenance
Kristoffer Thue | Crane Engineer | 2026-03-05 |  | 2026-03-25 | Destiny | SBM Offshore | Offshore | 281010-16 | Expat | Topside davits maintenance
Ivan Heredia | Project Engineer | 2025-11-19 |  | 2025-11-20 | Onshore | Axess Glass Inc | Travel | 282000-45 | Expat | Travel to MX
Ivan Heredia | Project Engineer | 2025-11-17 |  | 2025-11-18 | GYBSI | SBM Offshore | Onshore | 282000-44 | Expat | Ulva insulation scopes
Alistair Narain | Project Engineer | 2026-02-10 |  | 2026-02-12 | Nexus | SBM offshore | Onshore | 282000-83 | Local | Unity rigging loft control
Daniel Henry | Multiskilled rope access technician | 2026-02-10 |  | 2026-02-12 | Nexus | SBM offshore | Onshore | 282000-83 | Local | Unity rigging loft control
Darrel Cato | Multiskilled rope access technician | 2026-02-10 |  | 2026-02-12 | Nexus | SBM offshore | Onshore | 282000-83 | Local | Unity rigging loft control
Jared Gonsalves | Multiskilled rope access technician | 2026-02-10 |  | 2026-02-12 | Nexus | SBM offshore | Onshore | 282000-83 | Local | Unity rigging loft control
Paraisram Budhu | Multiskilled rope access technician | 2026-02-10 |  | 2026-02-12 | Nexus | SBM offshore | Onshore | 282000-83 | Local | Unity rigging loft control
Darrel Cato | Multiskilled rope access technician | 2025-11-06 |  | 2025-11-13 | Unity | SBM Offshore | Offshore | 282000-51 | Local | Water Injection shutdown
Hendrick Mallinson | Workleader | 2025-11-06 |  | 2025-12-04 | Unity | SBM Offshore | Offshore | 282000-51 | Expat | Water Injection shutdown
Iván Heredia | Workleader | 2026-02-26 |  | 2026-03-12 | Destiny | SBM offshore | Offshore | 281009-04 | Expat | Emergency Composite Wrap
TBC | Field Technician | 2026-02-26 |  | 2026-03-12 | Destiny | SBM offshore | Offshore | 281009-04 | Expat | Emergency Composite Wrap
Britney Benjamin | Field Technician | 2026-02-26 |  | 2026-03-12 | Destiny | SBM offshore | Offshore | 281009-04 | Expat | Emergency Composite Wrap
Raul Almeida | Workleader | 2026-01-01 |  | 2026-03-12 | Don Taylor | Noble | Offshore | 281001-19 | Expat | NDT / LGI
Alex Ali | Workleader | 2026-01-06 |  | 2026-02-03 | Don Taylor | Noble | Offshore | 281001-19 | Regional | NDT / LGI
Raul Almeida | Workleader | 2026-02-03 |  | 2026-03-03 | Don Taylor | Noble | Offshore | 281001-19 | Expat | NDT / LGI
Alvin Ong | Workleader | 2026-01-01 |  | 2026-01-16 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Andy Rahim | Workleader | 2026-01-16 |  | 2026-01-23 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Alvin Ong | Workleader | 2026-01-23 |  | 2026-03-06 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Jovin Franklin | Workleader | 2026-01-01 |  | 2026-01-10 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Gerardo Licona | Workleader | 2026-01-13 |  | 2026-02-13 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Jovin Franklin | Workleader | 2026-02-13 |  | 2026-03-10 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Ahmad Fathol | Workleader | 2026-01-01 |  | 2026-01-16 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Syahrizan Khaidzir | Workleader | 2026-01-16 |  | 2026-01-23 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Ahmad Fathol | Workleader | 2026-01-23 |  | 2026-02-27 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Alex Ali | Workleader | 2026-03-03 |  | 2026-04-03 | Don Taylor | Noble | Offshore | 281001-19 | Regional | NDT / LGI
Raul Almeida | Workleader | 2026-04-03 |  | 2026-05-01 | Don Taylor | Noble | Offshore | 281001-19 | Expat | NDT / LGI
Alex Ali | Workleader | 2026-05-01 |  | 2026-05-29 | Don Taylor | Noble | Offshore | 281001-19 | Regional | NDT / LGI
Raul Almeida | Workleader | 2026-05-29 |  | 2026-06-26 | Don Taylor | Noble | Offshore | 281001-19 | Expat | NDT / LGI
Alex Ali | Workleader | 2026-06-26 |  | 2026-07-24 | Don Taylor | Noble | Offshore | 281001-19 | Regional | NDT / LGI
Raul Almeida | Workleader | 2026-07-24 |  | 2026-08-21 | Don Taylor | Noble | Offshore | 281001-19 | Expat | NDT / LGI
Alex Ali | Workleader | 2026-08-21 |  | 2026-09-18 | Don Taylor | Noble | Offshore | 281001-19 | Regional | NDT / LGI
Raul Almeida | Workleader | 2026-09-18 |  | 2026-10-16 | Don Taylor | Noble | Offshore | 281001-19 | Expat | NDT / LGI
Alex Ali | Workleader | 2026-10-16 |  | 2026-11-13 | Don Taylor | Noble | Offshore | 281001-19 | Regional | NDT / LGI
Raul Almeida | Workleader | 2026-11-13 |  | 2026-12-11 | Don Taylor | Noble | Offshore | 281001-19 | Expat | NDT / LGI
Alex Ali | Workleader | 2026-12-11 |  | 2026-12-31 | Don Taylor | Noble | Offshore | 281001-19 | Regional | NDT / LGI
Andy Rahim | Workleader | 2026-03-06 |  | 2026-04-10 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Alvin Ong | Workleader | 2026-04-10 |  | 2026-05-08 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Andy Rahim | Workleader | 2026-05-08 |  | 2026-06-05 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Alvin Ong | Workleader | 2026-06-05 |  | 2026-07-03 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Andy Rahim | Workleader | 2026-07-03 |  | 2026-07-31 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Alvin Ong | Workleader | 2026-07-31 |  | 2026-08-28 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Andy Rahim | Workleader | 2026-08-28 |  | 2026-09-25 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Alvin Ong | Workleader | 2026-09-25 |  | 2026-10-23 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Andy Rahim | Workleader | 2026-10-23 |  | 2026-11-20 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Alvin Ong | Workleader | 2026-11-20 |  | 2026-12-18 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Andy Rahim | Workleader | 2026-12-18 |  | 2026-12-31 | Tom Madden | Noble | Offshore | 281002-19 | Expat | NDT / LGI
Gerardo Licona | Workleader | 2026-03-10 |  | 2026-04-07 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Jovin Franklin | Workleader | 2026-04-07 |  | 2026-05-05 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Gerardo Licona | Workleader | 2026-05-05 |  | 2026-06-02 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Jovin Franklin | Workleader | 2026-06-02 |  | 2026-06-30 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Gerardo Licona | Workleader | 2026-06-30 |  | 2026-07-28 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Jovin Franklin | Workleader | 2026-07-28 |  | 2026-08-25 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Gerardo Licona | Workleader | 2026-08-25 |  | 2026-09-22 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Jovin Franklin | Workleader | 2026-09-22 |  | 2026-10-20 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Gerardo Licona | Workleader | 2026-10-20 |  | 2026-11-17 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Jovin Franklin | Workleader | 2026-11-17 |  | 2026-12-15 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Gerardo Licona | Workleader | 2026-12-15 |  | 2026-12-31 | Sam Croft | Noble | Offshore | 281003-19 | Expat | NDT / LGI
Khairul Fasahrazni | Workleader | 2026-02-27 |  | 2026-03-20 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Ahmad Fathol | Workleader | 2026-03-20 |  | 2026-04-17 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Khairul Fasahrazni | Workleader | 2026-04-17 |  | 2026-05-15 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Ahmad Fathol | Workleader | 2026-05-15 |  | 2026-06-12 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Khairul Fasahrazni | Workleader | 2026-06-12 |  | 2026-07-10 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Ahmad Fathol | Workleader | 2026-07-10 |  | 2026-08-07 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Khairul Fasahrazni | Workleader | 2026-08-07 |  | 2026-09-04 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Ahmad Fathol | Workleader | 2026-09-04 |  | 2026-10-02 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Khairul Fasahrazni | Workleader | 2026-10-02 |  | 2026-10-30 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Ahmad Fathol | Workleader | 2026-10-30 |  | 2026-11-27 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Khairul Fasahrazni | Workleader | 2026-11-27 |  | 2026-12-25 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Ahmad Fathol | Workleader | 2026-12-25 |  | 2026-12-31 | Bob Douglas | Noble | Offshore | 281007-19 | Expat | NDT / LGI
Formulas:
End Date = Table1[[#This Row],[Start Date]]+[Duration (days)]-1

## Equipment planner
Description & ID | Start Date | End Date | Installation | Client | Status | Work Order | Scope
Eddy current SN N500X11290T071515 | 2025-12-18 | 2025-12-24 | Destiny | SBM offshore | On project | 282000-77 | GTG-200 davit inspection
MPI yoke SN N1547 | 2025-12-18 | 2025-12-24 | Destiny | SBM offshore | On project | 282000-77 | GTG-200 davit inspection
Pad eye tester green monster SN 25904584/18 | 2025-12-18 | 2025-12-27 | One Guyana | SBM offshore | On project | 282000-42 | 6M LGI
Manual torque wrench SN 23023561 | 2025-12-05 | 2025-12-24 | Destiny | SBM offshore | On project | 282000-77 | GTG-200 davit inspection
Rope access kit #1 | 2025-11-04 | 2025-11-06 |  |  |  | 281008-01 | 100T Mobile crane certification
| 2025-11-07 | 2025-11-09 |  |  |  | 281008-02 | 60T Mobile crane certification
| 2025-11-09 | 2025-11-09 |  |  |  | 281008-02 | 60T Mobile crane certification
| 2025-11-10 | 2025-11-14 |  |  |  | 281008-04 | 300T Mobile crane certification
| 2025-11-17 | 2025-11-18 |  |  |  | 282000-44 | Ulva insulation scopes
| 2025-11-19 | 2025-11-20 |  |  |  | 282000-45 | Travel to MX
| 2025-11-18 | 2026-01-03 |  |  |  | N/A | Rest period
| 2025-11-17 | 2025-11-27 |  |  |  | 281010-04 | Annual crane inspection
| 2025-12-03 | 2025-12-10 |  |  |  | 282000-58 | Annual elevator inspection
| 2025-12-11 | 2025-12-18 |  |  |  | 281010-10 | Annual crane inspection
| 2025-12-28 | 2026-01-01 |  |  |  | 281010-07 | Annual elevator inspection
| 2025-11-22 | 2025-11-26 |  |  |  | 282000-08 | Flare boom survey
| 2025-11-27 | 2025-12-01 |  |  |  | 282000-57 | Hull inspection survey
| 2025-12-08 | 2025-12-21 |  |  |  | 282000-26 | 6M LGI
| 2025-12-22 | 2025-01-11 |  |  |  | N/A | Rest period
| 2025-11-10 | 2025-11-13 |  |  |  | 282000-26 | Fall protection inspection
| 2025-11-16 | 2025-12-01 |  |  |  | 257020-05 | eDROPS
| 2025-12-02 | 2025-12-04 |  |  |  | N/A | Ulva training
| 2025-12-06 | 2025-12-27 |  |  |  | 282000-42 | 6M LGI
| 2025-11-10 | 2025-11-13 |  |  |  | 282000-26 | Fall protection inspection
| 2025-11-22 | 2025-12-03 |  |  |  | TBD | Maintenance scopes
| 2025-12-02 | 2025-12-04 |  |  |  | N/A | Ulva training
| 2025-12-08 | 2025-12-21 |  |  |  | 282000-26 | 6M LGI
| 2025-11-04 | 2025-12-05 |  |  |  | 281001-09 | Contractual scopes
| 2025-12-08 | 2025-12-29 |  |  |  | 619078-91 | eDROPS
| 2025-11-22 | 2025-12-03 |  |  |  | TBD | Maintenance scopes
| 2025-12-02 | 2025-12-04 |  |  |  | N/A | Ulva training
| 2025-12-08 | 2025-12-29 |  |  |  | 619078-91 | eDROPS
| 2025-10-21 | 2025-11-28 |  |  |  | 281001-10 | Exhaust fans scope
| 2025-12-02 | 2025-12-04 |  |  |  | N/A | Ulva training
| 2025-12-06 | 2025-12-27 |  |  |  | 282000-42 | 6M LGI
| 2025-11-16 | 2025-12-01 |  |  |  | 257020-05 | eDROPS
| 2025-12-02 | 2025-12-04 |  |  |  | N/A | Ulva training
| 2025-12-08 | 2025-12-21 |  |  |  | 282000-26 | 6M LGI
| 2025-10-21 | 2025-11-28 |  |  |  | 281001-10 | Exhaust fans scope
| 2025-12-02 | 2025-12-04 |  |  |  | N/A | Ulva training
| 2025-12-08 | 2025-12-29 |  |  |  | 619078-91 | eDROPS
| 2025-10-21 | 2025-11-21 |  |  |  | 281001-10 | Exhaust fans scope
| 2025-11-22 | 2025-12-03 |  |  |  | TBD | Maintenance scopes
| 2025-12-05 | 2025-12-07 |  |  |  | N/A | Ulva training
| 2025-12-08 | 2025-12-29 |  |  |  | 619078-91 | eDROPS
| 2025-11-17 | 2025-11-27 |  |  |  | 281010-04 | Annual crane inspection
| 2025-12-02 | 2025-12-04 |  |  |  | N/A | Ulva training
| 2025-12-06 | 2025-12-27 |  |  |  | 282000-42 | 6M LGI
| 2025-10-24 | 2025-11-15 |  |  |  | 281002-10 | Lifeboats inspection
| 2025-11-21 | 2025-12-12 |  |  |  | 281002-09 | Contractual scopes
| 2025-12-15 | 2025-12-29 |  |  |  | 282000-17 | 6M LGI
| 2025-11-06 | 2025-12-04 |  |  |  | 282000-51 | Water Injection shutdown
| 2025-12-05 | 2025-12-10 |  |  |  | TBD | 6M Crane certification
| 2025-12-11 | 2025-12-18 |  |  |  | 281010-10 | Annual crane inspection
| 2025-11-21 | 2025-11-28 |  |  |  | 281001-10 | Exhaust fans scope
| 2025-12-02 | 2025-12-04 |  |  |  | N/A | Ulva training
| 2025-12-05 | 2025-12-10 |  |  |  | TBD | 6M Crane certification
| 2025-12-15 | 2025-12-29 |  |  |  | 282000-17 | 6M LGI

## Lists
Status (list) | Support Classification (list) | Client | Installation | Equipment type | Calibration due date | Equipment status | Technician name | Designation
Offshore | Local | SBM offshore | Destiny | Rope access kit #1 | 2025-12-11 | On project | Darrel Cato | LEEA Inspector, RAT lvl 1, Rigger, DROPS, NDT Technician | Local
Onshore | Regional | Noble | Unity | Eddy current SN N500X11290T071515 | 10/28/2026 | In maintenance | Erick Peña | Crane Inspector, RAT lvl | Expat
Days Off | Expat | Solstad | Prosperity | MPI yoke SN N1547 |  | In calibration | Britney Benjamin | OPITO Rigger 1, Drone Pilot | Local
Travel |  | DOF | One Guyana | MPI coil |  | Out of service | Paraisram Budhu | NDT Technician | Local
Training |  | SAIPEM | Don Taylor | UV light |  |  | Alistair Naraim | LEEA Inspector | Local
Standby |  | Training | Tom Madden | PAUT |  |  | Akaysse de Silva | LEEA Inspector, RAT lvl 1, Rigger, DROPS, NDT Technician | Local
Annual leave |  | Axess Glass Inc | Bob Douglas | UTM |  |  | Shamir Chester | RAT lvl 1 | Local
Available |  |  | Sam Croft | UT shearwave |  |  | Jared Gonsalves | RAT lvl 1 | Local
|  |  | Normand Samson | 12T load cell |  |  | Raghvendra Singh | Advanced NDT Inspector, RAT lvl 1 | Expat
|  |  | Veshi yard | 55T load cell |  |  | Ivan Heredia | Mechanical Lead, RAT lvl 1, DROPS, NDT Technician, ULVA Technician | Expat
|  |  | Castorone | Pad eye tester parker |  |  | Alex Ali | Work Leader, NDT technician, RAT lvl 3 | Regional
|  |  | GYBSI | Pad eye tester green monster SN 25904584/18 | 2026-04-01 |  | Raul Almeida | Work Leader, Advanced NDT technician, RAT lvl 3, | Expat
|  |  | Nomad | Pad eye tester sling max |  |  | Arul Franklin | Work Leader, NDT technician, RAT lvl 3 | Expat
|  |  | Errea Wittu | Drone Matrice 30T |  |  | Gerardo Licona | Work Leader, NDT technician, RAT lvl 2 | Expat
|  |  | Jaguar | Magnetic rope testing AMC-40 |  |  | Ahmad Fayazdami | Work Leader, NDT technician, RAT lvl 1 | Expat
|  |  | Costellation | Pneumatic toque pistol J-Gun-3 |  |  | Khayrul Fasahrazni | Work Leader, NDT technician, RAT lvl 3 | Expat
|  |  | FDS-2 | Pneumatic toque pistol J-Gun-5 |  |  | Alvin Ong | Work Leader, NDT technician, RAT lvl 3 | Expat
|  |  | Onshore | Pneumatic regulator & filter kit |  |  | Heryandy Rahim | Work Leader, NDT technician, RAT lvl 3 | Expat
|  |  | Nexus | Pneumatic regulator & filter kit |  |  | Conrad Westhuizen | RBI Technician, RAT lvl 3 | Expat
|  |  |  | Pneumatic regulator & filter kit |  |  | Syahrizan Khaidzir | Work Leader, NDT technician, RAT lvl 3, MRT | Expat
|  |  |  | Pneumatic regulator & filter kit |  |  | Jesus Hidalgo | NDT Technician, RAT lvl 1 | Expat
|  |  |  | Pneumatic hose |  |  | Leonardo Gonzaga | NDT Technician, RAT lvl 1, OPITO Scaffolder, NDT Technician | Expat
|  |  |  | Pneumatic hose |  |  | Jesus Estrada | NDT technician, RAT lvl 3 | Expat
|  |  |  | Pneumatic hose |  |  | Lee Poh Chew | RAT lvl 3, OPITO Rigger 1, Derrick builder | Expat
|  |  |  | Pneumatic hose |  |  | Nio Ann Aik | RAT lvl 3, OPITO Rigger 1, Derrick builder | Expat
|  |  |  | Crane inspetion kit |  |  | Roy Musa | Work Leader, RAT lvl 3, OPITO Rigger, Derrick builder | Expat
|  |  |  | EX phone |  |  | Huan Peng Whee | RAT lvl 3, NDT Technician | Expat
|  |  |  | EX phone |  |  | Lee Poh Seng | RAT lvl 3, OPITO Rigger 1, Derrick builder | Expat
|  |  |  | Digital camera |  |  | Jaylano Toppin | RAT lvl 1, NDT Technician | Regional
|  |  |  | Digital camera |  |  | Oscar Fernandez | Drone Pilot | Expat
|  |  |  | Digital camera |  |  | Zammam Houssam | Elevator Inspector, Crane Inspector, API RP 2D | Expat
|  |  |  | EX tablet Dell |  |  | Edwin Abraham | NACE/FROSIO Inspector | Expat
|  |  |  | EX tablet Dell |  |  | Nicholas Ramlogan | RAT lvl 2, NDT Technician | Regional
|  |  |  | EX tablet Dell |  |  | Yousef Alqwaiwi | Elevator Inspector | Expat
|  |  |  | EX tablet Dell |  |  | Dillon Harry | RAT lvl 1, Advanced NDT Inspector | Regional
|  |  |  | LGI kit #1 |  |  | Kenneth Brandal | Crane Inspector, RAT lvl 3 | Expat
|  |  |  | LGI kit #2 |  |  | Alexander McLeary | ULVA Technician, RAT lvl 3 | Expat
|  |  |  | LGI kit #3 |  |  | Kristoffer Thiue | Crane Inspector, RAT lvl | Expat
|  |  |  | LGI kit #4 |  |  | Ivar Hestnes | Crane Inspector, RAT lvl | Expat
|  |  |  | Rope access kit #2 |  |  | Saeed Abrahams |  | Expat
|  |  |  | Rope access kit #3 |  |  | Riki Basri |  | Expat
|  |  |  | Rope access kit #4 |  |  | Donovan Abrahams | RAT lvl 3, OPITO Rigger 4, pipe fitter | Expat
|  |  |  | Rope access kit #5 |  |  | Warren Williams | RAT lvl 1, Pipe fitter | Expat
|  |  |  | Rope access kit #6 |  |  | Franck Matteolli | RBI Technician | Expat
|  |  |  | Rope access kit #7 |  |  | Gladstone Johnson | NDT Technician, RAT lvl 1 | Regional
|  |  |  | Rope access kit #8 |  |  | Shivanan Gordeen | NDT Technician, RAT lvl 1 | Regional
|  |  |  | C-Claw toolkit |  |  | Hendrick Mallison | Work Leader, NDT technician, RAT lvl 3, Crane Inspector, OPITO Rigger 3 | Expat
|  |  |  | Manual torque wrench SN 23023561 | 2026-07-08 |  | Edgar Dorantes | EX Technician, RAT lvl 1 | Expat
[7 empty] | Kyle Figaro | Work Leader, RAT lvl 3 | Expat
[7 empty] | Paul Thompson | Work Leader, NDT technician, RAT lvl 3, Crane Inspector, OPITO Rigger 3 | Expat
[7 empty] | Mawabo Dumezweni | RAT lvl 3, OPITO Rigger 4, pipe fitter | Expat

## Examples
Technician Name | Competency | Start Date | End Date | Installation | Client | Status | Work Order | Support Classification
John Doe | Level 2 Rope Access | 2025-01-03 | 2025-01-15 | MODEC – FPSO | MODEC | Offshore | WO-9876 | Regional
Viviana Quijano | NDT – UT 2 | 2025-01-16 | 2025-01-22 | SBM – FPSO | SBM | Training / Standby | WO-9882 | Expat
Erick Peña | Inspector – L3 | 2025-01-10 | 2025-01-25 | SAIPEM – MODU | SAIPEM | Onshore | WO-9850 | Local

## README
Instructions
PERSONNEL PLANNER – DATA ENTRY GUIDE
Objective: Capture personnel assignments to visualize utilization and location (offshore/onshore/days off/travel/training).
Sheets:
- Planner: Fill this sheet ONLY. 50 empty rows prepared. Do not add columns.
- Lists: Controlled vocabularies for dropdowns (Status, Support Classification). Do not edit names or headers.
- Examples: 3 sample rows showing the expected format.
Required fields (per row): Technician Name, Start Date, End Date, Status.
Date format: YYYY-MM-DD (e.g., 2025-02-14).
Validation rules:
- End Date must be the same or after Start Date.
- Status must be one of the dropdown options.
- Support Classification must be one of: Local, Regional, Expat.
Notes:
- Work Order is optional but recommended for traceability.
- Installation and Client help drive drilldowns in Power BI.
- Do not use merged cells or additional formatting in the Planner sheet.
Power BI Tips (for the data team):
- Import the Planner sheet as a table.
- Relate Start/End dates to your Date table via a daily-expanded bridge (optional) to enable Gantt/heatmaps.
- Use slicers on Status, Client, Installation, Support Classification.